IMPLEMENTATION & DEVELOPMENT PLAN

Integrated POS, Inventory & Business Management System

Java 21 • Spring Boot 3.x • PostgreSQL • React/Next.js

| Document Information | Value |
| --- | --- |
| Document Type | Implementation & Development Plan |
| Version | 1.0 |
| Status | Development Baseline |
| Backend | Java 21 LTS + Spring Boot 3.x |
| Database | PostgreSQL + Flyway |
| Frontend | React / Next.js + TypeScript |
| Infrastructure | Docker + Nginx + CI/CD |
| Source Documents | PRD • SRS • SAD • Database • REST API • UI/UX |
| Date | 25 August 2026 |

# 1. Purpose

This document converts the approved product, requirements, architecture, database, API, and UI/UX specifications into an executable development roadmap. It defines project setup, engineering practices, implementation phases, dependencies, testing, deployment, milestones, and Definition of Done.

# 2. Development Strategy

Build the MVP as a modular Spring Boot monolith backed by PostgreSQL.

Develop backend and frontend incrementally around vertical business workflows rather than isolated technical layers.

Prioritize the complete POS transaction loop early: product → cart → payment → inventory → register → receipt.

Use automated tests from the beginning.

Keep every feature traceable to an SRS requirement and API/UI contract.

Delay advanced integrations and microservice extraction until the core store workflow is stable.

# 3. Target Technology Stack

| Area | Technology |
| --- | --- |
| Language | Java 21 LTS |
| Backend | Spring Boot 3.x |
| Security | Spring Security + JWT |
| Persistence | Spring Data JPA / Hibernate |
| Database | PostgreSQL |
| Migration | Flyway |
| Cache | Redis |
| API | REST + JSON |
| API Documentation | OpenAPI / Swagger |
| Build | Maven |
| Backend Testing | JUnit 5, Mockito, Spring Boot Test, Testcontainers |
| Frontend | React / Next.js + TypeScript |
| Frontend Testing | Vitest/Jest + Testing Library + Playwright |
| Containerization | Docker / Docker Compose |
| Reverse Proxy | Nginx |
| CI/CD | GitHub Actions or equivalent |
| Source Control | Git + GitHub |

# 4. Project Repository Structure

pos-system/
├── backend/
│   ├── src/main/java/com/pos/
│   ├── src/main/resources/
│   ├── src/test/
│   ├── pom.xml
│   └── Dockerfile
├── frontend/
│   ├── src/
│   ├── public/
│   ├── package.json
│   └── Dockerfile
├── database/
│   └── migrations/
├── infra/
│   ├── docker/
│   ├── nginx/
│   └── compose/
├── docs/
└── .github/
    └── workflows/

# 5. Git & Branching Strategy

main
  │
  ├── develop
  │    ├── feature/auth
  │    ├── feature/products
  │    ├── feature/inventory
  │    └── feature/pos
  │
  └── release/*
       └── hotfix/*

main contains production-ready code.

develop contains integrated development work if a team workflow requires it.

Feature branches should be short-lived and focused on one capability.

Pull requests require review and automated CI checks.

Production hotfixes must be merged back into development branches.

Commit messages should be concise and meaningful.

# 6. Coding Standards

| Area | Standard |
| --- | --- |
| Java | Google Java Format or agreed Spring/Java style; clear naming and small methods. |
| Spring | Constructor injection; avoid field injection. |
| DTOs | Never expose JPA entities directly through REST. |
| Transactions | Place @Transactional boundaries in application services. |
| Errors | Use centralized exception handling with @RestControllerAdvice. |
| Validation | Use Jakarta Bean Validation and domain validation. |
| Money | Use BigDecimal. |
| Database | Use Flyway migrations; avoid uncontrolled schema changes. |
| Frontend | TypeScript strict mode; reusable components. |
| API | Follow the REST API Specification exactly. |
| Tests | Test business rules and critical workflows, not only controllers. |

# 7. Development Environments

| Environment | Purpose |
| --- | --- |
| Local | Developer implementation and unit/integration testing. |
| CI | Automated compile, test, lint/static analysis, security checks. |
| Development | Shared integrated feature testing. |
| Staging | Production-like acceptance and release validation. |
| Production | Live store/business operation. |

Each environment must have separate configuration and secrets.

Production data must never be used in development without approved anonymization.

Database migrations must be applied consistently across environments.

# 8. Initial Project Setup

Create Git repository and protected main branch.

Initialize Spring Boot backend with Java 21 and Maven.

Initialize React/Next.js TypeScript frontend.

Configure PostgreSQL and Flyway.

Configure Docker Compose for local services.

Configure environment variables and secret templates.

Configure global logging, error handling, validation, and API response conventions.

Configure OpenAPI documentation.

Configure CI pipeline.

Create baseline README and development documentation.

# 9. Development Phases

| Phase | Focus | Estimated Duration* |
| --- | --- | --- |
| Phase 0 | Project foundation & tooling | 1 week |
| Phase 1 | Authentication, RBAC & organization | 1–2 weeks |
| Phase 2 | Products & catalog | 1–2 weeks |
| Phase 3 | Inventory & stock control | 2 weeks |
| Phase 4 | Customers & suppliers | 1–2 weeks |
| Phase 5 | Purchasing & accounts payable | 2 weeks |
| Phase 6 | POS sales & payments | 2–3 weeks |
| Phase 7 | Cash register & day-end | 1 week |
| Phase 8 | Returns, quotations & promotions | 2 weeks |
| Phase 9 | Online orders | 1–2 weeks |
| Phase 10 | Budgets & reporting | 2 weeks |
| Phase 11 | Hardening, security & performance | 2 weeks |
| Phase 12 | Staging, UAT & production launch | 1–2 weeks |

*Estimates assume focused development and are planning ranges, not guaranteed delivery dates. Parallel work by multiple developers can reduce calendar time.

# 10. Phase 0 — Foundation

Repository and branching strategy.

Spring Boot project structure.

Frontend project structure.

PostgreSQL/Flyway baseline.

Docker Compose.

Common API response/error format.

Global exception handling.

Logging and correlation IDs.

OpenAPI setup.

CI pipeline.

Base design system and frontend routing.

## Definition of Done

Backend builds successfully.

Frontend builds successfully.

Database migrations run cleanly.

CI passes.

Local environment can be started using documented commands.

# 11. Phase 1 — Authentication, RBAC & Organization

Users, roles, permissions.

Login, refresh, logout.

Store access scope.

Stores, terminals, registers.

Register session foundation.

Admin user screens.

| Backend Deliverables | Frontend Deliverables |
| --- | --- |
| Auth endpoints | Login screen |
| JWT/security filters | Protected routes |
| User/role repositories/services | User management |
| Store/terminal/register APIs | Store/terminal administration |
| Authorization tests | Permission-aware navigation |

# 12. Phase 2 — Products & Catalog

Categories, brands, units.

Products and SKUs.

Barcodes.

Prices and pricing history.

Product activation/deactivation.

Catalog search APIs.

The product catalog should be stable before POS development begins because product identity and pricing are foundational to inventory and sales.

# 13. Phase 3 — Inventory

Inventory balances.

Inventory transaction ledger.

Stock receiving.

Adjustments.

Transfers.

Batch/lot tracking.

Expiration tracking.

Low-stock alerts.

Inventory reports.

## Critical Test Scenarios

Concurrent sales cannot corrupt stock.

Adjustment requires reason and permission.

Receiving increases stock correctly.

Expiry filters return correct batches.

Negative stock behavior follows configuration.

# 14. Phase 4 — Customers & Suppliers

Customer profiles and history.

Store credit ledger.

Supplier profiles.

Supplier-product associations.

Search and filtering.

# 15. Phase 5 — Purchasing & Accounts Payable

Purchase order lifecycle.

Goods receiving.

Supplier invoices.

Outstanding/overdue payables.

Partial supplier payments.

Supplier statements.

Purchase Order → Goods Receipt → Supplier Invoice → Accounts Payable → Supplier Payment

# 16. Phase 6 — POS Sales & Payments

This is the primary MVP business milestone.

POS layout implementation.

Product/barcode lookup.

Cart operations.

Customer selection.

Discount calculation.

Tax calculation.

Payment methods.

Split payments if enabled.

Sale completion.

Inventory deduction.

Receipt generation.

Idempotency and duplicate-submit protection.

## Critical Transaction

Sale + Sale Items + Payments + Inventory Movement + Register Transaction + Audit = ONE controlled business transaction

# 17. Phase 7 — Cash Register & Day-End

Open register session.

Opening cash.

Cash-in/cash-out.

Session summary.

Expected cash calculation.

Actual cash count.

Variance.

Z report.

Session locking after close.

# 18. Phase 8 — Returns, Quotations & Promotions

Return/refund workflow.

Refund eligibility.

Quotation lifecycle.

Quotation-to-sale conversion.

Percentage/fixed discounts.

Promotion rules.

Promotion dates.

Stacking/priority rules.

Discount permission controls.

# 19. Phase 9 — Online Orders

External order ingestion.

Idempotency.

Order queue.

Order status transitions.

Inventory reservation strategy.

Cancellation.

Refund integration.

Fulfillment workflow.

The external channel adapter must be isolated from core POS domain logic.

# 20. Phase 10 — Budgets & Reporting

Budget creation and approval.

Expense recording.

Budget vs actual.

Sales reports.

Inventory reports.

Cash register reports.

Accounts payable reports.

Profit/financial reports where supported.

Export functionality.

# 21. Phase 11 — Security & Performance Hardening

Dependency vulnerability scan.

Authentication security tests.

Authorization/privilege escalation tests.

Input validation/security tests.

SQL injection and API abuse tests.

Rate limiting.

Load testing.

POS transaction concurrency testing.

Database query optimization.

Logging/monitoring verification.

# 22. Phase 12 — Staging, UAT & Production

Deploy release candidate to staging.

Run database migrations.

Run automated test suite.

Run UAT scenarios.

Validate POS hardware integrations.

Validate receipt/label printing.

Validate register closing.

Validate backup and restore.

Resolve release-blocking defects.

Create production release.

Deploy with rollback plan.

Perform smoke tests.

Begin monitored production operation.

# 23. MVP Scope

| Module | MVP |
| --- | --- |
| Authentication/RBAC | ✓ |
| Stores/Terminals/Registers | ✓ |
| Products/Catalog | ✓ |
| Inventory | ✓ |
| Stock Alerts | ✓ |
| Customers | ✓ |
| Suppliers | ✓ |
| Purchasing | ✓ |
| Accounts Payable | ✓ |
| POS Sales | ✓ |
| Payments | ✓ |
| Returns/Refunds | ✓ |
| Cash Register | ✓ |
| Day-End Closing | ✓ |
| Receipts | ✓ |
| Basic Reports | ✓ |
| Audit Logs | ✓ |
| Quotations | Recommended |
| Promotions | Recommended |
| Online Orders | Phase 2 if schedule is constrained |
| Budgets | Phase 2 |

# 24. Suggested Sprint Structure

| Sprint | Primary Goal |
| --- | --- |
| Sprint 1 | Foundation, repositories, CI/CD, Docker, database baseline. |
| Sprint 2 | Authentication, users, roles, permissions, stores. |
| Sprint 3 | Terminals, registers, product catalog. |
| Sprint 4 | Inventory balances, movements, adjustments. |
| Sprint 5 | Receiving, batches, expiry, stock alerts. |
| Sprint 6 | Customers, store credits, suppliers. |
| Sprint 7 | Purchasing and AP. |
| Sprint 8 | POS checkout, payments, receipts. |
| Sprint 9 | Returns, register closing, day-end. |
| Sprint 10 | Quotations, promotions. |
| Sprint 11 | Online orders, budgets. |
| Sprint 12 | Reports, hardening, UAT preparation. |
| Sprint 13 | UAT fixes, production readiness. |

A sprint can be 1–2 weeks depending on team size and working agreement.

# 25. Backend Development Workflow

Requirement
   ↓
API Contract
   ↓
DTO + Validation
   ↓
Service / Business Logic
   ↓
Repository
   ↓
Migration
   ↓
Unit Tests
   ↓
Integration Tests
   ↓
API Tests
   ↓
Pull Request
   ↓
CI
   ↓
Review

# 26. Frontend Development Workflow

UI/UX Specification
       ↓
Reusable Components
       ↓
Page / Feature
       ↓
API Client
       ↓
Loading / Error / Empty States
       ↓
Permission Handling
       ↓
Component Tests
       ↓
E2E Workflow Tests
       ↓
Review / CI

# 27. Testing Strategy

| Test Level | Coverage |
| --- | --- |
| Unit | Business calculations, validation, promotion rules, register calculations. |
| Repository | Database mappings, constraints, query behavior. |
| Integration | Transactional workflows across modules. |
| API | HTTP contracts, authorization, validation, error responses. |
| Frontend | Components, forms, state, accessibility. |
| E2E | Complete POS, receiving, AP, register closing workflows. |
| Concurrency | Inventory and transaction conflict scenarios. |
| Performance | Checkout, product search, reporting, concurrent users. |
| Security | Authentication, authorization, injection, abuse, secrets. |

# 28. Critical End-to-End Test Cases

Login as cashier → open register → scan product → cash payment → receipt.

Cashier → sell multiple products → verify inventory deduction.

Cashier → apply authorized discount → verify totals.

Cashier → process return → verify refund and stock.

Inventory manager → receive purchase → verify inventory.

Inventory manager → adjust damaged stock → verify ledger and audit.

Accountant → create supplier invoice → partial payment → verify remaining payable.

Cashier → cash-in/cash-out → close register → verify variance.

Manager → create promotion → checkout eligible product → verify promotion.

Online order → ingest twice with same external ID → verify one order.

Unauthorized cashier → attempt privileged refund/adjustment → verify 403.

# 29. CI/CD Pipeline

Pull Request
   ↓
Checkout
   ↓
Dependency Install
   ↓
Compile / Build
   ↓
Unit Tests
   ↓
Integration Tests
   ↓
Static Analysis
   ↓
Security Scan
   ↓
Docker Build
   ↓
Artifact/Image
   ↓
Staging Deploy
   ↓
Smoke Tests

Production deployment should require an approved release.

Database migrations should be part of controlled deployment.

Production deployment must have a rollback strategy.

# 30. Deployment Plan

| Component | Deployment |
| --- | --- |
| Frontend | Static/Node deployment behind Nginx or managed hosting. |
| Spring Boot | Docker container(s) behind Nginx/load balancer. |
| PostgreSQL | Managed PostgreSQL or dedicated secured database server. |
| Redis | Managed Redis or secured container/service. |
| Backups | Automated PostgreSQL backup with separate storage. |
| Monitoring | Application metrics, logs, health checks, alerting. |

# 31. Production Readiness Checklist

Security review complete.

All critical tests passing.

No critical/high unresolved defects.

Database backup verified.

Restore procedure tested.

TLS configured.

Secrets managed securely.

Production configuration reviewed.

Monitoring and alerting active.

Receipt/label hardware validated.

Register/day-end workflow validated.

Rollback plan documented.

User roles and store permissions verified.

Support/runbook documentation prepared.

# 32. Definition of Ready

Requirement has an approved SRS reference.

API contract is defined.

UI/UX behavior is defined.

Database impact is understood.

Acceptance criteria are testable.

Dependencies are identified.

Security implications are understood.

# 33. Definition of Done

Implementation matches approved requirement.

Code reviewed and merged.

Database migration included if required.

Unit tests pass.

Integration/API tests pass.

Frontend states are implemented.

Authorization is verified.

Audit requirements are implemented.

API documentation is updated.

Acceptance criteria pass.

No critical/high defect remains for release scope.

# 34. Team Responsibilities

| Role | Responsibilities |
| --- | --- |
| Product Owner | Requirements, priorities, acceptance, business decisions. |
| Project Manager | Planning, risks, schedule, coordination. |
| Tech Lead | Architecture, code standards, technical decisions, reviews. |
| Backend Developer | Spring Boot modules, APIs, database integration, tests. |
| Frontend Developer | POS/admin UI, API integration, UX implementation, tests. |
| QA Engineer | Test strategy, test cases, regression, UAT support. |
| UI/UX Designer | Design system, screens, workflows, usability. |
| DevOps Engineer | CI/CD, Docker, environments, monitoring, deployment. |

# 35. Risk Management

| Risk | Mitigation |
| --- | --- |
| Scope expansion | Freeze MVP scope and use change-control process. |
| Inventory inconsistency | Strict transactions, concurrency tests, inventory ledger. |
| Financial calculation errors | BigDecimal, centralized calculation rules, extensive tests. |
| Hardware compatibility | Hardware abstraction and early device testing. |
| Security vulnerabilities | Security review, automated scans, least privilege. |
| Slow reports | Dedicated reporting queries, indexes, async generation if needed. |
| Premature microservices | Keep modular monolith until measurable need. |
| Data loss | Automated backups and restore tests. |
| Poor cashier adoption | Usability testing with realistic POS workflows. |

# 36. Project Milestones

| Milestone | Outcome |
| --- | --- |
| M1 Foundation Complete | Repositories, environments, CI, database, base frontend. |
| M2 Identity & Catalog | Users, RBAC, stores, terminals, products. |
| M3 Inventory Ready | Stock, receiving, expiry, alerts. |
| M4 Financial Operations | Purchasing, AP, customers, credits. |
| M5 POS MVP | Checkout, payments, inventory deduction, receipts. |
| M6 Store Operations | Returns, registers, day-end. |
| M7 Business Features | Promotions, quotations, orders, budgets. |
| M8 Reporting & Hardening | Reports, security, performance. |
| M9 Production Ready | UAT, hardware validation, backups, deployment. |

# 37. Estimated MVP Timeline

For a small focused team, a realistic initial production MVP is approximately **12–18 weeks**, depending on team size, hardware/payment integrations, business-rule complexity, testing depth, and whether online ordering/budgets are included in the first release.

| Team Profile | Indicative Calendar |
| --- | --- |
| 1 full-stack developer | Longer; approximately 5–8 months for a robust MVP. |
| 2 developers + QA part-time | Approximately 3–5 months. |
| Backend + frontend + QA + DevOps | Approximately 12–18 weeks. |
| Larger parallel team | Potentially shorter, but coordination and integration effort increase. |

These are planning estimates only. The POS, inventory, accounting, and hardware workflows should be validated before committing to a fixed launch date.

# 38. Phase 2 & Phase 3 Roadmap

| Phase | Potential Features |
| --- | --- |
| Phase 2 | Advanced online orders, advanced promotions, budgets, richer reports, loyalty, multi-store transfers, mobile management. |
| Phase 3 | Full accounting/GL, advanced analytics, demand forecasting, warehouse management, advanced integrations, service-oriented extraction where justified. |

# 39. First Development Sprint — Detailed Tasks

| Area | Tasks |
| --- | --- |
| Backend | Create Spring Boot app, packages, configuration, health endpoint, exception framework. |
| Database | PostgreSQL connection, Flyway baseline, identity/store tables. |
| Security | Spring Security, JWT flow, password hashing. |
| Frontend | Next.js/React app, routing, layout, design tokens. |
| DevOps | Docker Compose, local PostgreSQL/Redis, CI workflow. |
| Testing | JUnit setup, Testcontainers setup, frontend test setup. |
| Documentation | README, environment setup, contribution guide. |

# 40. Next Steps

Approve this implementation plan.

Create the Git repository.

Create backend and frontend projects.

Set up PostgreSQL/Flyway and Docker.

Implement authentication and RBAC foundation.

Begin Sprint 1 and maintain requirement/API/UI traceability.

PRD → SRS → SAD → Database → REST API → UI/UX → Implementation Plan → DEVELOPMENT

END OF IMPLEMENTATION & DEVELOPMENT PLAN